## PESO-Link
SYSTEM QUALITY ASSURANCE AND DEPLOYMENT READINESS TRACKER
Instruction: Select a development status for every feature. Modify the user role/checklist as needed by adding, removing, or renaming features to match the actual functionalities of your system.
No. | User Role | Feature or Module | Status | QA Result | QA Findings or Issues | Action Required | QA Date
1 | System Wide | Android frontend TypeScript/lint readiness pending full deployment validation | Under Development | Not Yet Tested
2 | System Wide | Backend API source syntax and route loading pending live MySQL validation | Under Development | Not Yet Tested
3 | System Wide | MySQL schema, seed data, and live database readiness | Under Development | Not Yet Tested
4 | System Wide | Android deployment/APK build artifact configuration | Under Development | Not Yet Tested
5 | System Wide | Backend URL and LAN phone testing configuration | Under Development | Not Yet Tested
6 | System Wide | Suspended-account login blocking and active-session enforcement | Under Development | Not Yet Tested
7 | Job Seeker | Self-registration, login, logout, and role-based routing | Under Development | Not Yet Tested
8 | Job Seeker | NSRP-based profile creation/editing pending official NSRP field-completeness validation | Under Development | Not Yet Tested
9 | Job Seeker | Skills selection for profile and saved skill set | Under Development | Not Yet Tested
10 | Job Seeker | OCR-assisted NSRP image upload or camera capture pending live-device/API validation | Under Development | Not Yet Tested
11 | Job Seeker | OCR extraction review, manual editing, and confirmed save pending real-form OCR validation | Under Development | Not Yet Tested
12 | Job Seeker | Active job vacancy browsing | Under Development | Not Yet Tested
13 | Job Seeker | Keyword search and job-type filtering | Under Development | Not Yet Tested
14 | Job Seeker | Location filtering in the Job Seeker interface | Under Development | Not Yet Tested
15 | Job Seeker | Job details, employer details, and application instructions pending application/referral wording cleanup | Under Development | Not Yet Tested
16 | Job Seeker | Rule-based matched/missing skill comparison pending end-to-end validation | Under Development | Not Yet Tested
17 | Job Seeker | Application submission flow pending job-specific PESO referral alignment | Under Development | Not Yet Tested
18 | Job Seeker | Duplicate application prevention and application detail records | Under Development | Not Yet Tested
19 | Job Seeker | My Applications status tracking pending PESO-Referred alignment | Under Development | Not Yet Tested
20 | Job Seeker | In-app notification list and read status | Under Development | Not Yet Tested
21 | Employer | Login through PESO Admin-created employer account | Under Development | Not Yet Tested
22 | Employer | Create and update job postings with requirements and skills | Under Development | Not Yet Tested
23 | Employer | Close job postings while retaining monitoring records | Under Development | Not Yet Tested
24 | Employer | View applicants with NSRP summary pending PESO-Referred endorsement alignment | Under Development | Not Yet Tested
25 | Employer | Update current application tracking status pending PESO-Referred alignment | Under Development | Not Yet Tested
26 | PESO Admin | Dashboard and monitoring overview | Under Development | Not Yet Tested
27 | PESO Admin | Create and list PESO Admin-created employer accounts | Under Development | Not Yet Tested
28 | PESO Admin | Manage job seeker accounts and deactivate/reactivate users | Under Development | Not Yet Tested
29 | PESO Admin | Monitor and close job postings | Under Development | Not Yet Tested
30 | PESO Admin | NSRP profile review UI and Referral-Ready/Needs Revision controls | Under Development | Not Yet Tested
31 | PESO Admin | Job-specific PESO referral routing and endorsement workflow | Not Yet Implemented | Not Yet Tested
32 | PESO Admin | PESO Admin application monitoring pending referral processing controls | Under Development | Not Yet Tested
33 | System Wide | PESO-Referred per-application status/label handling | Not Yet Implemented | Not Yet Tested
34 | System Wide | Application submitted/pending status history consistency | Under Development | Not Yet Tested
35 | PESO Admin | Legacy employer approval/rejection workflow cleanup | Under Development | Not Yet Tested
36 | System Wide | Live MySQL/API regression testing with seeded three roles | Under Development | Not Yet Tested

## Lists
Status | QA Result
Ready to Deploy | Passed
Under Development | Passed with Minor Issues
Not Yet Implemented | Needs Revision
Failed
Not Yet Tested